## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Laying of Pipe line Construction of Pump House & B/Wall at 3rd Site of SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000148/2023-2024 | 858/CD | 21/08/2023 | 18/01/2024 | MS SSB CONSTRUCTION CO | 121.49 | 0 | 0 | 61
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Providing FHTC & Laying of Pipe line of SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000149/2023-2024 | 857/CD | 21/08/2023 | 20/10/2023 | M/S. NITYAGOPAL BANIK | 145.55 | 23.45 | 16.11 | 95
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Providing FHTC & Laying of Pipe line of SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000150/2023-2024 | 856/CD | 21/08/2023 | 20/10/2023 | MATARA CONSTRUCTION CO. | 109.25 | 50.55 | 46.27 | 65
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Construction of 450 cum OHR and Laying of Pipe line at SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000151/2023-2024 | 855/CD | 21/08/2023 | 18/01/2024 | GHOSH AND SAHA CONSTRUCTION | 276.33 | 0 | 0 | 45
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Execution of different works related to AUG. of Shikarpur Zone-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000154/2023-2024 | 854/CD | 21/08/2023 | 18/01/2024 | AMBITIOUS ENTERPRISE | 450.34 | 46.04 | 10.22 | 18
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Sinking of Big Dia Tubewell at HWSite & 2nd Site of SHIKARPUR PWSS under JAL JEEVAN MISSION (Z-I : 3rd Site Z-II : HW & 2nd Site | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000155/2023-2024 | 853/CD | 21/08/2023 | 19/11/2023 | MATARA CONSTRUCTION CO. | 35.05 | 32.01 | 91.34 | 92
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Providing FHTC and Laying of Pipe line of SHIKARPUR ZONE ? II PWSS under JAL JEEVAN MISSION (PART ?D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000156/2023-2024 | 865/CD | 22/08/2023 | 20/11/2023 | M/S NARAYAN KR. GHOSH | 83.42 | 0 | 0 | 65
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Execution of different works related to SIKARPUR PWSS under JAL JEEVAN MISSION MKG | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER | ORD/000488/2023-2024 | 290/CD | 09/02/2024 | 09/04/2024 | M/S SURAJIT MAJUMDER | 5.06 | 0 | 0 | 100
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Execution of different works related to SHIKARPUR PWSS under JAL JEEVAN MISSION MTB |  |  | ORD/000606/2023-2024 | 652/CD | 11/03/2024 | 10/05/2024 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 25.02 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 254/CD | 27/04/2023 |  | Resource Division | 39.47 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF SIKARPUR Water Supply Scheme TW No.- I of Zone-I and I and II of Zone-II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001091/2023-2024 | 2810/NMD-II | 09/10/2023 | 08/11/2023 | M/S SAJAHAN CHOWDHURY | 31.75 | 13.23 | 41.65 | 40
Total | [13 empty] | 21112.03 | 165.27 | 0.78