## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Sherpur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Raiganj,Capacity- 90 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000003/2021-2022 | 1208/RD/PHE | 18/06/2021 | 16/09/2021 | M/S LOKENATH CONSTRUCTION | 37.36 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Supplying, Laying, Fixing and Jointing of UPVC Pipe including Dismantling PCC & Ordinary Cement Concrete [1:2:4] in connection with retrofitting of FHTC under TUNGAIL BILLPARA & Adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division ,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000108/2020-2021 | 475/RD/PHE | 26/02/2021 | 28/03/2021 | M/S.SADHANA ENTERPRISE | 6.36 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Puria and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000126/2020-2021 | 362/RD/PHE | 04/02/2021 | 16/03/2021 | UTTAM SAHA | 91.12 | 0 | 0 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Gutin and adjoining Mouzas Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000135/2020-2021 | 1528/RD/PHE | 23/12/2020 | 06/02/2021 | M/S LOKENATH CONST | 101.7 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at under Baruna and adjoining Mouza Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000137/2020-2021 | 1527/RD/PHE | 23/12/2020 | 06/02/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 104.88 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Tungail Bilpara and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000139/2020-2021 | 1524/RD/PHE | 23/12/2020 | 06/02/2021 | SANYAL ENTERPRISE | 110.26 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Gopalpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000140/2020-2021 | 1533/RD/PHE | 23/12/2020 | 06/02/2021 | M/S LOKENATH CONST | 110.89 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Dakhin Jibakata and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000141/2020-2021 | 1540/RD/PHE | 23/12/2020 | 06/02/2021 | CALCON CONSTRUCTION | 126.63 | 0 | 0 | 100
9 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Sitgram and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000143/2020-2021 | 1537/RD/PHE | 23/12/2020 | 06/02/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 103.65 | 0 | 0 | 15
10 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Bamair and adjoining Mouzas Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000144/2020-2021 | 1531/RD/PHE | 23/12/2020 | 06/02/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 116.81 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | FHTC OF MAHINAGAR WSS |  |  | ORD/000159/2020-2021 | 1504/RD | 23/12/2020 | 17/01/2021 | M/S ARVI CONSTRUCTION | 3.06 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | FHTC OF GOPALPUR WSS |  |  | ORD/000160/2020-2021 | 1502/RD | 23/12/2020 | 17/01/2021 | KARTICK BISWAS | 1.8 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Pokheria and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000165/2020-2021 | 374/RD/PHE | 05/02/2021 | 02/03/2021 | SARNALI ENTERPRISE | 3.36 | 0 | 0 | 1
14 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Sridharpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000166/2020-2021 | 375/RD/PHE | 05/02/2021 | 02/03/2021 | GOPES SAHA | 3.33 | 0 | 0 | 1
15 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kaliganj and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000172/2020-2021 | 1544/RD/PHE | 23/12/2020 | 01/02/2021 | NEOGI ENTERPRISE | 98.37 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Sridharpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000173/2020-2021 | 1526/RD/PHE | 23/12/2020 | 06/02/2021 | AJIT PARMANIK | 126.43 | 0 | 0 | 0
17 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Bindol and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000174/2020-2021 | 1529/RD/PHE | 23/12/2020 | 06/02/2021 | AJIT PARMANIK | 125.64 | 0 | 0 | 0
18 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Mahinagar and adjoining Mouzas Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000175/2020-2021 | 1543/RD/PHE | 23/12/2020 | 01/02/2021 | SANYAL ENTERPRISE | 96.95 | 0 | 0 | 0
19 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Deona and adjoining Mouzas Water Supply Scheme in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000177/2020-2021 | 1542/RD/PHE | 23/12/2020 | 01/02/2021 | MAMATA USHA ENTERPRISE | 94.51 | 0 | 0 | 0
20 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Laying of Additional Pipe Line for improving FHTC nos. of Jaingaon Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000186/2022-2023 | 2256/RD/PHE | 22/12/2022 | 21/01/2023 | APEX ENTERPRISES RUPESH.RNJ@GMAIL.COM | 5.75 | 0 | 0 | 0
21 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Gunabari and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000203/2020-2021 | 1534 /RD/PHE | 23/12/2020 | 06/02/2021 | M/S LOKENATH CONSTRUCTION | 122.2 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Jaingaon and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000204/2020-2021 | 1538/RD/PHE | 23/12/2020 | 06/02/2021 | M/S SOMNATH KUNDU | 104.31 | 0 | 0 | 90
23 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Pokheria and adjoining Mouzas Water Supply Scheme in Goalpoklher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000205/2020-2021 | 1530/RD/PHE | 23/12/2020 | 06/02/2021 | AJIT PARMANIK | 134.73 | 0 | 0 | 50
24 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Poaltair and adjoining Mouzas water supply scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000209/2020-2021 | 1539/RD/PHE | 23/12/2020 | 06/02/2021 | SANYAL ENTERPRISE | 106.28 | 0 | 0 | 0
25 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Phulatti and adjoining mouzas Water Supply Scheme in Kaliaganj Block in under Raiganj Division.(Part-III) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000236/2020-2021 | 476/RD/PHE | 26/02/2021 | 12/04/2021 | SUBHAS CHOWDHURY | 4.1 | 0 | 0 | 0
26 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at under Bheur and adjoining Mouza Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000277/2020-2021 | 1557/RD/PHE | 24/12/2020 | 22/02/2021 | UTTAM SAHA | 124.33 | 0 | 0 | 100
27 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER PAHARAJPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN ITAHAR BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000278/2020-2021 | 1560/RD/PHE | 24/12/2020 | 22/02/2021 | J.D.J. ENTERPRISE | 133.31 | 0 | 0 | 0
28 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER BHAGABATI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN CHOPRA BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000279/2020-2021 | 1564/RD/PHE | 24/12/2020 | 22/02/2021 | M/S LOKENATH CONSTRUCTION | 194.09 | 0 | 0 | 0
29 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Bheur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000279/2022-2023 | 493/RD/PHE | 17/02/2023 | 03/04/2023 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 6.22 | 0 | 0 | 0
30 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Laying of Additional Pipe Line for Providing Functional Household Tap Connection for Sridharpur(Paharajpur) Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD |  | ORD/000286/2022-2023 | 500/RD/PHE | 17/02/2023 | 03/04/2023 | SANDIP SARKAR | 7.18 | 0 | 0 | 0
31 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING AND JOINTING UPVC PIPE INCLUDING DISMANTLING PCC FHTC OF GUTIN PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000367/2020-2021 | 1514/RD | 23/12/2020 | 22/01/2021 | M/S.BANGARAJ | 9.92 | 0 | 0 | 0
32 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Jaingaon for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000434/2021-2022 | 2196/RD/PHE | 17/11/2021 | 17/12/2021 | M/S SARKAR ENTERPRISE | 44.62 | 0 | 0 | 0
33 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING OF FHTC OF JAINGAON PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000440/2020-2021 | 1498/RD | 23/12/2020 | 17/01/2021 | DULAL MAJUMDER | 3.82 | 0 | 0 | 0
34 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING OF FHTC OF GUNABARI PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000441/2020-2021 | 1499/RD | 23/12/2020 | 17/01/2021 | M/S GHOSH CONSTRUCTION | 2.5 | 0 | 0 | 0
35 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | SUPPLYING FITTING UPVC PIPE FOR KALIGANJ PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000447/2020-2021 | 1503/RD | 23/12/2020 | 17/01/2021 | ALI ENTERPRISE | 2.75 | 0 | 0 | 0
36 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Restoration of damaged Pipe Line work required for FHTC work at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000452/2021-2022 | 2428/RD/PHE | 31/12/2021 | 30/01/2022 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.87 | 0 | 0 | 100
37 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | supply, laying, fitting , fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1;2:4) for FHTC under Bhagabati and adjoining mouzas water supply scheme in chopra block under Raiganj Division, P.h.e.dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000463/2020-2021 | 1509/RD/PHE | 23/12/2020 | 22/01/2021 | PRINCE BUILDERS | 8.31 | 0 | 0 | 0
38 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING AND JOINTING OF UPVC PIPE INCLUDING DISMANTLING PCC OF FHTC OF DEONA PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000464/2020-2021 | 1507/RD | 23/12/2020 | 22/01/2021 | M/S LUCKY CONSTRUCTION | 11.66 | 0 | 0 | 0
39 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING AND JOINTING UPVC PIPE INCLUDING DISMANTLING PCC FHTC OF BAMAIR PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000465/2020-2021 | 1508/RD/PHE | 23/12/2020 | 22/01/2021 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.91 | 0 | 0 | 0
40 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | office accessories bill |  |  | VCH/000312/2022-2023 | BP-2022-23-36 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.13 | 0 | 0 | 0
41 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | office accessories bill |  |  | VCH/000325/2022-2023 | BP-2022-23-28 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
42 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | office accessories bill |  |  | VCH/000327/2022-2023 | BP-2022-23-26 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0 | 0
43 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Supply of urgent office article against laying of additional pipeline Siripur |  |  | VCH/001438/2022-2023 | BP-2022-23-158 | 28/09/2022 | 28/09/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
44 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | Supply of urgent office article against laying of additional pipeline Siripur |  |  | VCH/001440/2022-2023 | BP-2022-23-159 | 28/09/2022 | 28/09/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
45 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07390 | Retrofitting | hire charge of vehicle |  |  | VCH/001732/2022-2023 | BP-2022-23-137 | 12/09/2022 | 12/09/2022 | DIGENDRANATH DAS | 0.04 | 0 | 0 | 0
Total | [13 empty] | 2503.56 | 0 | 0