## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. | SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS UNDER RAIGANJ DIVISION, P.H.E.DTE. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000077/2022-2023 | GEMC-511687724974541 | 28/05/2022 | 27/06/2022 | IONET | 11.54 | 0.21 | 1.82 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. | SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS |  |  | VCH/000413/2022-2023 | BP-2022-23-50 | 12/05/2022 |  | IONET | 2.79 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. | SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS |  |  | VCH/000414/2022-2023 | BP-2022-23-46 | 12/05/2022 |  | IONET | 0.75 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. | SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS |  |  | VCH/000415/2022-2023 | BP-2022-23-47 | 12/05/2022 |  | IONET | 2.75 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. | SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS |  |  | VCH/000416/2022-2023 | BP-2022-23-48 | 12/05/2022 |  | IONET | 4.3 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. | SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS |  |  | VCH/000417/2022-2023 | BP-2022-23-49 | 12/05/2022 |  | IONET | 0.72 | 0 | 0 | 0
Total | [13 empty] | 22.85 | 0.21 | 0.92