## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Raiganj District Water Testing Laboratory under the Executive Engineer, Raiganj Division, PHE Dte, Government of West Bengal. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000037/2021-2022 | 1560/RD/PHE | 04/08/2021 | 19/08/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 20.3 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipment's, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Raiganj District Water Testing Laboratory under the Executive Engineer, Raiganj Division, PHE Dte, Government of West Bengal. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000042/2021-2022 | 1687/RD/PHE | 26/08/2021 | 10/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 20.3 | 4.86 | 23.94 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in dist lab |  |  | VCH/001902/2022-2023 | BP-2022-23-241 | 25/11/2022 |  | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab |  |  | VCH/001903/2022-2023 | BP-2022-23-242 | 25/11/2022 |  | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab |  |  | VCH/001904/2022-2023 | BP-2022-23-243 | 25/11/2022 |  | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab |  |  | VCH/001905/2022-2023 | BP-2022-23-240 | 25/11/2022 |  | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab |  |  | VCH/001906/2022-2023 | BP-2022-23-238 | 25/11/2022 |  | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen | SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab |  |  | VCH/001907/2022-2023 | BP-2022-23-239 | 25/11/2022 |  | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
Total | [13 empty] | 41.19 | 4.86 | 11.8