## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Construction of Pump House at 3rd tubewell Site (3.60mx3.00m ) Raghabpur Piped Water Supply Scheme in connection with Augmentation of Raghabpur PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD |  | ORD/000041/2023-2024 | 1540/RD/PHE | 24/05/2023 | 23/07/2023 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 4.09 | 2.01 | 49.09 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Augmentation of RAGHABPUR Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000103/2022-2023 | 1550/RD/PHE | 26/08/2022 | 24/11/2022 | DIPESH BHOWMIK | 144.6 | 127.36 | 88.08 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | FHTC (Functional Household Tap Connection) for Raghabpur Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000162/2022-2023 | 2022/RD/PHE | 17/11/2022 | 15/02/2023 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 53.39 | 17.69 | 33.14 | 70
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of RAGHABPUR Pipe Water Supply Scheme in connection with Augmentation at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000210/2022-2023 | 79/RD/PHE | 17/01/2023 | 14/09/2023 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 86.06 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000238/2022-2023 | 371/RD/PHE | 07/02/2023 | 24/03/2023 | D. K. ASSOCIATES BISWAJITKAR9434@GMAIL.COM | 4.96 | 2.47 | 49.78 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Repairing of Pump House at 2nd Tubewell site in connection with Augmentation of RAGHABPUR Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000239/2022-2023 | 372/RD/PHE | 07/02/2023 | 24/03/2023 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.02 | 1 | 49.63 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Repairing of Pump House at 3rd Tubewell site in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000252/2022-2023 | 380/RD/PHE | 07/02/2023 | 24/03/2023 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.06 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 1943/RD/PHE | 04/11/2022 |  | Resource Division | 20.88 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Raghabpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011648) | Assistant Engineer - I |  | ORD/000612/2023-2024 | 2654/MLMD | 10/08/2023 | 06/11/2028 | DAS CONSTRUCTION | 10.55 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001051/2022-2023 | 0252/MLMD | 24/02/2023 | 25/05/2023 | DEB CONSTRUCTION. | 10.36 | 4.99 | 48.13 | 100
11 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001052/2022-2023 | 253/MLMD | 24/02/2023 | 25/05/2023 | S.P. ENTERPRISE (KOLKATA) | 10.45 | 10.44 | 99.93 | 100
12 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001053/2022-2023 | 254/MLMD | 24/02/2023 | 25/05/2023 | FUTURE | 10.55 | 9.62 | 91.16 | 100
13 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Raghabpur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001160/2022-2023 | 4003118806 | 26/03/2023 | 02/04/2023 | W.B.S.E.D.C.LTD | 0.55 | 0.55 | 100 | 0
14 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | SM/11728 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Raghabpur PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001940/2023-2024 | 4003266667 | 23/11/2023 | 21/02/2024 | W.B.S.E.D.C.LTD | 6.4 | 3.2 | 50 | 100
Total | [13 empty] | 366.92 | 179.33 | 48.87