## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Augmentation of PANJIPARA (Zone-I)Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000104/2022-2023 | 1551/RD/PHE | 26/08/2022 | 24/11/2022 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 162.49 | 113.07 | 69.58 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site, & 3rd Tube-Well Site under Augmentation of Panjipara PWSS at Goalpukhur-I Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000160/2024-2025 | 2892/RD/PHE | 25/09/2024 | 24/03/2025 | HAQUE CONSTRUCTION | 26.07 | 0 | 0 | 60
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | FHTC (Functional Household Tap Connection) for Panjipara Zone-I Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000164/2022-2023 | 2024/RD/PHE | 17/11/2022 | 05/08/2025 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 82.85 | 32.56 | 39.29 | 40
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000243/2022-2023 | 374/RD/PHE | 07/02/2023 | 24/03/2023 | M/S PAYEL CONSTRUCTION HIMADRI.RNJ@GMAIL.COM | 5.01 | 4.96 | 98.92 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Repair Pump House 2nd Tube well & 3rd Tubewell Site in connection with Augmentation of Panjipara Zone-I piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000247/2022-2023 | 377/RD/PHE | 07/02/2023 | 31/07/2024 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 2.1 | 0 | 0 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of PANJIPARA (Zone-I) Pipe Water Supply Scheme in connection with Augmentation at Goalpokher-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000379/2022-2023 | 734/RD/PHE | 15/03/2023 | 10/12/2024 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 143.15 | 80.3 | 56.09 | 80
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Providing FHTC at Panjipara Santinagar of Panjipara Zone-I PWSS in connection with Augmentation of Panjipara Zone-I PWSS in Goalpukhur-I Block of Uttar Dinajpur under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000415/2023-2024 | 2787/RD/PHE | 11/10/2023 | 10/11/2023 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 2.87 | 2.8 | 97.39 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Balance pipeline with dismantling of concrete road in connection with Augmentation Of Panjipara Zone-I PWSS at Goalpukhur-I Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000513/2024-2025 | 44/RD/PHE | 03/01/2025 | 17/02/2025 | M/S J.M.M. CONSTRUCTION | 22.75 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Laying additional pipe line with FHTC for Augmentation of Panjipara Zone-I Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division., P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000515/2024-2025 | 3801/RD/PHE | 20/12/2024 | 18/06/2025 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 28.73 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Laying additional pipe line with FHTC for Augmentation of Panjipara Zone-I Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division., P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000516/2024-2025 | 3802/RD/PHE | 20/12/2024 | 03/02/2025 | M/S BHOWMIK ENTERPRISE | 28.73 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000568/2022-2023 | 1031/RD/PHE | 31/03/2023 | 16/08/2024 | M/S PAYEL CONSTRUCTION HIMADRI.RNJ@GMAIL.COM | 4.1 | 0 | 0 | 100
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 1972/RD/PHE | 08/11/2022 | 08/11/2022 | Resource Division | 142.48 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Panjipara Water Supply Scheme (Zone-I) TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000015/2023-2024 | 771/MLMD | 26/04/2023 | 21/01/2024 | MANIK CHANDRA SAHA. | 11.45 | 6.24 | 54.46 | 100
15 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Panjipara, Zone-I, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000089/2023-2024 | 4003160435 | 17/05/2023 | 16/05/2024 | W.B.S.E.D.C.LTD | 19.87 | 19.87 | 100 | 0
16 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No.- I of Augmentation of Panjipara (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011666) | Assistant Engineer - I | Junior Engineer-02 | ORD/000206/2023-2024 | 2131/MLMD | 07/07/2023 | 03/10/2028 | SUBHAS CHANDRA KESHORI | 6.97 | 0 | 0 | 0
17 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | SM/11800 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Panjipara Water Supply Scheme (Zone-I) TW no II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001092/2022-2023 | 263/MLMD | 24/02/2023 | 25/05/2023 | DIPALI CONSTRUCTION. | 11.47 | 10.31 | 89.92 | 0
Total | [13 empty] | 705.91 | 270.09 | 38.26