## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Hiring of vehicle for transportation of water sample collection from different BPHC to district lab uttar dinajpur |  |  | BILL/01085/2023-2024 | BP-2023-24-274 | 09/02/2024 | 09/02/2024 | FARHAD ALI | 0.05 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Bhelagachhi PWSS at Islampur Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000161/2024-2025 | 2893/RD/PHE | 25/09/2024 | 15/10/2024 | GOPES SAHA | 6.18 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Implementation of BHELAGACHHI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000329/2022-2023 | 670/RD/PHE | 06/03/2023 | 31/10/2024 | M/S LOKENATH CONSTRUCTION | 581.2 | 300.25 | 51.66 | 65
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BHELAGACHHI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000373/2024-2025 | 3492/RD/PHE | 02/12/2024 | 16/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 79.83 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Trial Run For Bhelagachi PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000716/2024-2025 | 548/RD/PHE | 12/02/2025 | 13/05/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 606/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 42.2 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Additional Quotation for new service connection at BHELAGACCHI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00023/2024-2025 | BP-2024-25-40 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 5.28 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Quotation for new service connection at Bhelagacchi PH-II (Islampur ccc) district Uttar Dinajpur. |  |  | BILL/03561/2023-2024 | BP-2023-24-591 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 7.31 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhelagachhi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017356) | Assistant Engineer - I | Junior Engineer-02 | ORD/000461/2023-2024 | 2480/MLMD | 04/08/2023 | 26/11/2024 | ANIMA ENTERPRISE | 26.45 | 20.35 | 76.93 | 100
10 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BELAGACHHI, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001511/2023-2024 | 4003195371 | 18/07/2023 | 16/10/2023 | W.B.S.E.D.C.LTD | 10.69 | 10.69 | 100 | 100
Total | [13 empty] | 760.05 | 331.28 | 43.59