## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara & adjoining mouzas for Purba Kalikapur Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000042/2020-2021 | 1856/BD | 07/12/2020 | 11/01/2021 | CHOUDHURY CONSTRUCTION | 7.68 | 7.25 | 94.4 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara & its adjoining Mouzas for Laskarpur Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer Hili | ORD/000044/2020-2021 | 1864/BD | 07/12/2020 | 21/01/2021 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 14.52 | 10.4 | 71.61 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara & its adjoining Mouzas for Dhalpara Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000045/2020-2021 | 1865/BD | 07/12/2020 | 21/01/2021 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 16.51 | 16.37 | 99.15 | 1
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara and adjoining mouzas for Purba Gobindapur Mouja at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000050/2020-2021 | 1886/BD | 07/12/2020 | 11/01/2021 | RABIN KAMETH | 3.6 | 2.19 | 60.78 | 1
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara and adjoining mouzas for Srikrishnapur Mouja at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000062/2020-2021 | 1973/BD | 18/12/2020 | 22/01/2021 | MAYA CONSTRUCTION | 4.45 | 4.38 | 98.47 | 1
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara and adjoining mouzas for Uttar Jamalpur Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000072/2020-2021 | 2038/BD | 29/12/2020 | 02/02/2021 | SHYAMAL CHANDRA MONDAL. | 6.13 | 5.33 | 87.03 | 1
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection (F.H.T.C) for 5 (Five) Numbers of Mouza under Dhalpara PWSS Under Jal Swapna Programme at Hili Block under Balurghat Division P.H. Engineering Dte. in the District of Dakshin Dinajpur |  | Junior Engineer Hili | ORD/000262/2021-2022 | 2561/BD | 09/11/2021 | 19/12/2021 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 8.08 | 7.44 | 92.06 | 1
Total | [13 empty] | 60.97 | 53.36 | 87.52