## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - IV under Tapan Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000079/2023-2024 | 893/BD | 25/07/2023 | 24/08/2023 | M/S. BANI CONSTRUCTIUON | 4.55 | 1.71 | 37.56 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - VI under Tapan Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000105/2023-2024 | 1247/BD | 24/08/2023 | 23/09/2023 | MAA CHANCHALA CONSTRUCTION | 4.52 | 0.19 | 4.21 | 100
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Providing Functional House Hold Tap connection work by Retrofitting of Zone- II at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000150/2022-2023 | 2864/BD | 05/01/2023 | 06/03/2023 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 63.68 | 46.8 | 73.48 | 55
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Providing Functional House Hold Tap connection work by Retrofitting of Zone- IV at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division | ORD/000151/2022-2023 | 2851/BD | 02/01/2023 | 03/03/2023 | NEOGI ENTERPRISE | 61.1 | 30.1 | 49.27 | 65
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Providing Functional House Hold Tap connection work by Retrofitting of Zone- V at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division | ORD/000152/2022-2023 | 2852/BD | 02/01/2023 | 03/03/2023 | ALOK ENTERPRISE | 74.44 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Providing Functional House Hold Tap connection work by Retrofitting of Zone- VI at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000153/2022-2023 | 2849/BD | 02/01/2023 | 03/03/2023 | SHYAMAL SHIL | 62.77 | 44.78 | 71.34 | 100
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Providing Functional House Hold Tap connection work by Retrofitting of Zone- I of Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000154/2022-2023 | 2850/BD | 02/01/2023 | 16/02/2023 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 26.55 | 23.33 | 87.86 | 62
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Laying of HDPE pipeline (for drinking water purpose) by using Horizontal Direct Drilling (HDD) method at different location on Tapan Kardaha Road & Kardaha Vikahar Road under Zone- IV of Tapan Sub Surface based Piped Water Supply Scheme at Tapan Block in the district of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000182/2022-2023 | 3290/BD | 09/02/2023 | 11/03/2023 | SAJEDUR RAHAMAN | 4.49 | 2.23 | 49.58 | 100
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Construction of approach road from main road to H/W site (outside portion) and allied work for 05 nos Zones of Tapan Western sector under Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000189/2022-2023 | 3516/BD | 04/03/2023 | 03/04/2023 | J. CHATTERJEEE & CO. | 23 | 22.25 | 96.73 | 0
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Construction of Support Structure with placing of GI pipe at various Khari crossing and Culvert Crossing of Distribution Pipeline of different place under Zone-I of Tapan Western Sector under Tapan Sub-Surface water based Piped Water Supply Scheme in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000199/2022-2023 | 3521/BD | 04/03/2023 | 03/04/2023 | M/S. SARKAR CONSTRUCTION | 12.48 | 10.58 | 84.81 | 100
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Various Piped Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. (Part I) |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division | ORD/000349/2021-2022 | 1927/BSSD | 01/12/2021 | 26/12/2021 | RADHARANI ENTERPRISE. | 4.79 | 4.66 | 97.33 | 100
12 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Various Piped Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. (Part II) | Assistant Engineer HQ | Junior Engineer 3 | ORD/000350/2021-2022 | 1928/BSSD | 01/12/2021 | 08/01/2022 | AJANTA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.84 | 4.78 | 98.92 | 0
13 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 3537/BD | 10/03/2023 |  | Resource Division | 40.35 | 0 | 0 | 0
Total | [13 empty] | 387.58 | 191.42 | 49.39