## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Arrangement of Running water source by sinking of 100 mm.X 50 mm. dia. Tube well including supply of Submersible Pump, PVC Pipe, , PVC Water tank & other Electro Mechanical accessories with installation for the 69 Nos. school having electricity Out Side the Command are of any PWSS of Balurghat Block in the district of Dakshin Dinajpur District, under Balurghat Division, PHE Dte. (PART-I). |  | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer Hili | ORD/000029/2022-2023 | 890/BD | 20/05/2022 | 04/07/2022 | DUTTA ENTERPRISE | 86.05 | 41.62 | 48.36 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Arrangement of Running water source by sinking of 100 mm.X 50 mm. dia. Tube well including supply of Submersible Pump, PVC Pipe, , PVC Water tank & other Electro Mechanical accessories with installation for the 69 Nos. school having electricity Out Side the Command are of any PWSS of Balurghat Block in the district of Dakshin Dinajpur District, under Balurghat Division, PHE Dte. (PART-II). |  | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer Hili | ORD/000030/2022-2023 | 891/BD | 20/05/2022 | 04/07/2022 | M/S. DAS CONSTRUCTION | 85.19 | 78.68 | 92.36 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Arrangement of Running water source by sinking of 100 mm.X 50 mm. dia. Tube well including supply of Submersible Pump, PVC Pipe, , PVC Water tank & other Electro Mechanical accessories with installation for the 51 Nos. school having electricity Out Side the Command are of any PWSS of Tapan Block in the district of Dakshin Dinajpur District, under Balurghat Division, PHE Dte. (PART-I). |  | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer Hili | ORD/000034/2022-2023 | 887/BD | 20/05/2022 | 04/07/2022 | M/S. ANWESHA ENTERPRISE | 69.09 | 63.45 | 91.85 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Arrangement of Running water source by sinking of 100 mm.X 50 mm. dia. Tube well including supply of Submersible Pump, PVC Pipe, , PVC Water tank & other Electro Mechanical accessories with installation for the 51 Nos. school having electricity Out Side the Command are of any PWSS of Tapan Block in the district of Dakshin Dinajpur District, under Balurghat Division, PHE Dte. (PART-II) |  | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer Hili | ORD/000035/2022-2023 | 888/BD | 20/05/2022 | 04/07/2022 | M/S. ANWESHA ENTERPRISE | 69.12 | 65.38 | 94.59 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Arrangement of Running water source by sinking of 100 mm.X 50 mm. dia. Tube well including supply of Submersible Pump, PVC Pipe, , PVC Water tank & other Electro Mechanical accessories with installation for the 15 Nos. school having electricity Out Side the Command are of any PWSS of Hili Block in the district of Dakshin Dinajpur District, under Balurghat Division, PHE Dte. |  | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer Hili | ORD/000036/2022-2023 | 892/BD | 20/05/2022 | 04/07/2022 | NARENDRANATH PAUL | 18.35 | 15.91 | 86.69 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 2587/BD | 09/12/2022 |  | Resource Division | 16.81 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Material Requisition To Resource Division |  |  | RTOR000053/2021-2022 | 451/BD | 16/03/2022 |  | Resource Division | 49.72 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Material Requisition To Resource Division |  |  | RTOR000054/2021-2022 | 452/BD | 16/03/2022 |  | Resource Division | 51 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Material Requisition To Resource Division |  |  | RTOR000055/2021-2022 | 453/BD | 16/03/2022 |  | Resource Division | 60.85 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Material Requisition To Resource Division |  |  | RTOR000056/2021-2022 | 454/BD | 16/03/2022 |  | Resource Division | 19.11 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | School | Material Requisition To Resource Division |  |  | RTOR000057/2021-2022 | 455/BD | 16/03/2022 |  | Resource Division | 11.18 | 0 | 0 | 0
Total | [13 empty] | 536.45 | 265.04 | 49.41