## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10453 | Retrofitting | Providing Functional House Hold Tap Connection in connection with Retrofitting for Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000067/2023-2024 | 816/BD | 13/07/2023 | 12/08/2023 | KRISHNA PAUL | 12.2 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10453 | Retrofitting | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Balurghat | ORD/000112/2022-2023 | 526/BD | 01/04/2022 | 01/05/2022 | M/S. SOBHA & CO. | 3.04 | 3.04 | 100 | 1
Total | [13 empty] | 15.24 | 3.04 | 19.96