## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10456 | Retrofitting | Consultancy Service for Preparation of DPR followed by detail Survey and design of pipe line network for Augmentation of Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.E. Dte. | Assistant Engineer HQ | Junior Engineer Hili | ORD/000374/2022-2023 | 897/BD | 23/05/2022 | 22/06/2022 | ENVIROTECH SOLUTIONS | 3.72 | 1.8 | 48.2 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10456 | Retrofitting | Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under various Piped Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur. | Assistant Engineer RWS | Junior Engineer Hili | ORD/000393/2021-2022 | 594/RWS | 31/12/2021 | 30/01/2022 | BALURGHAT BUILDERS | 4.61 | 4.09 | 88.67 | 100
Total | [13 empty] | 8.33 | 5.88 | 70.58