## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-XV by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 3 Sub Division | ORD/000024/2023-2024 | 315/BD | 15/05/2023 | 14/07/2023 | SUBODH KUMAR SAHA | 85.66 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-VIII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer Tapan | ORD/000034/2023-2024 | 452/BD | 01/06/2023 | 31/07/2023 | KHITISH KARMAKAR | 92.95 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-IX by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer Tapan | ORD/000036/2023-2024 | 440/BD | 31/05/2023 | 30/07/2023 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 95.24 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-XII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | ORD/000102/2023-2024 | 1133/BD | 11/08/2023 | 10/10/2023 | CHIRANJIB DAS | 87.92 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap Connection of Zone-III by Retrofitting of Tapan Eastern Sector under Sub - Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur | Assistant Engineer HQ | Junior Engineer HQ1 | ORD/000104/2023-2024 | 1143/BD | 14/08/2023 | 28/10/2023 | CHOWDHURY CONSTRUCTION | 94.7 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Widenning and strengthing of existing road for movement of heavy vehicle near WTP and towards Intake well site of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000226/2022-2023 | 3831/BD | 24/03/2023 | 13/04/2023 | B M CONSTRUCTION | 2.68 | 2.67 | 99.65 | 1
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-XIII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer Tapan | ORD/000234/2022-2023 | 3902/BD | 29/03/2023 | 28/05/2023 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 64.4 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-XIV by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer Tapan | ORD/000242/2022-2023 | 3925/BD | 30/03/2023 | 29/05/2023 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 76.54 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-VII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000245/2022-2023 | 3943/BD | 31/03/2023 | 30/05/2023 | NILKAMAL BASAK | 82.45 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-XI by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer Tapan | ORD/000254/2022-2023 | 3964/BD | 31/03/2023 | 30/05/2023 | NARENDRANATH PAUL | 69.1 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | Retrofitting | Providing Functional House Hold Tap connection of Zone-X by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000255/2022-2023 | 3963/BD | 31/03/2023 | 30/05/2023 | TARAMA CONSTRUCTION | 69.71 | 0 | 0 | 0
Total | [13 empty] | 821.35 | 2.67 | 0.33