## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 08/04/2024 | GHOSH BROTHERS | 2425.67 | 66.41 | 2.74 | 30
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2903/BD | 06/01/2023 |  | Resource Division | 17.62 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Payment for the quotation of New Connection of PH NO-II of DURLABHPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur |  |  | BILL/00033/2024-2025 | BP-2024-25-60 | 09/04/2024 |  | W.B.S.E.D.C.LTD | 6.51 | 0 | 0 | null
4 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Payment for the quotation of New Connection of PH NO-I , DURLABHPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur |  |  | BILL/00034/2024-2025 | BP-2024-25-61 | 09/04/2024 |  | W.B.S.E.D.C.LTD | 3.28 | 0 | 0 | null
5 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Durllabhpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013547) | Assistant Engineer - I | Junior Engineer-01 | ORD/001805/2023-2024 | 3692/MLMD | 29/11/2023 | 27/05/2024 | MERCURY ENGINEERING COMPANY. | 28.26 | 0 | 0 | 0
Total | [13 empty] | 2481.34 | 66.41 | 2.68