## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | TRIKUL Piped Water Supply Scheme | SM/12817 | New | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 08/04/2024 | GHOSH BROTHERS | 2425.67 | 0 | 0 | 30
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | TRIKUL Piped Water Supply Scheme | SM/12817 | New | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 2899/BD | 06/01/2023 |  | Resource Division | 8.82 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | TRIKUL Piped Water Supply Scheme | SM/12817 | New | Payment for the quotation of New Connection of PH NO-I of Trikul PWSS under Balurghat CCC in the District of Dakshin Dinajpur |  |  | BILL/03728/2023-2024 | BP-2023-24-698 | 18/03/2024 |  | W.B.S.E.D.C.LTD | 5.79 | 0 | 0 | null
4 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | TRIKUL Piped Water Supply Scheme | SM/12817 | New | Payment for the quotation of New Connection of PH NO-II of Trikul PWSS under Balurghat CCC in the District of Dakshin Dinajpur |  |  | BILL/03729/2023-2024 | BP-2023-24-699 | 18/03/2024 |  | W.B.S.E.D.C.LTD | 6.43 | 0 | 0 | null
5 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | TRIKUL Piped Water Supply Scheme | SM/12817 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Trikul Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014305) | Assistant Engineer - I | Junior Engineer-01 | ORD/000800/2023-2024 | 2560/MLMD | 04/08/2023 | 02/12/2023 | M/S. KUNDU CONSTRACTION | 26.56 | 8.78 | 33.06 | 70
Total | [13 empty] | 2473.27 | 8.78 | 0.35