## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Retrofitting of Bilbarail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-III] | SM/13018 | Retrofitting | Providing left out Functional House Hold Tap connection to make all the villages Swajal Gram with allied pipe line under BILBARAIL Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur. | Assistant Engineer Sadar | Junior Engineer 1 HQ | ORD/000183/2022-2023 | 3291/BD | 09/02/2023 | 11/03/2023 | SATELLITE CONSTRUCTION | 9.33 | 8.57 | 91.78 | 99
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Retrofitting of Bilbarail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-III] | SM/13018 | Retrofitting | Acceptance cum Work Order for the work of Land Devlopment by the Carried Earth including Construction of approach Road for Headworks site and 2nd Tubewell Site of BILBARAIL PWSS at Banshihari Block in the District of Dakshin Dinajpr under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 3 | ORD/000368/2021-2022 | 2858/BD | 16/12/2021 | 15/01/2022 | M/S. SARKAR CONSTRUCTION | 6.96 | 3.12 | 44.82 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Retrofitting of Bilbarail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-III] | SM/13018 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 10/BD | 04/04/2023 |  | Resource Division | 0.72 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Retrofitting of Bilbarail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-III] | SM/13018 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 842/BD | 14/07/2023 |  | Resource Division | 0.72 | 0 | 0 | 0
Total | [13 empty] | 17.74 | 11.69 | 65.89