## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line for providing FHTC in connection with Retrofitting of Kail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) | SM/15169 | Augmentation | Formal Work Order for the work of "Providing Functional House Hold Tap Connection for KAIL piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte." | Assistant Engineer HQ | Junior Engineer (Civil) | ORD/000007/2020-2021 | 1372/BD | 29/09/2020 | 13/11/2020 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.22 | 2.72 | 6.6 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line for providing FHTC in connection with Retrofitting of Kail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) | SM/15169 | Augmentation | Restoration of damaged pipe line and allied works under Retrofitting of Kail PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000007/2023-2024 | 272/BD | 05/05/2023 | 04/06/2023 | M/S. GHOSH ENTERPRISE | 2.03 | 0 | 0 | 90
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line for providing FHTC in connection with Retrofitting of Kail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) | SM/15169 | Augmentation | Allied Work In Connection With Providing Functional House Hold Tap Connection For Kail PWSS Under Jal Swapna Programme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer 3 Sub Division | ORD/000358/2021-2022 | 547/RWS | 03/12/2021 | 18/12/2021 | AMITAVA MITRA CONTRACTOR & ORDER SUPPLIER | 0.78 | 0.78 | 99.98 | 100
Total | [13 empty] | 44.03 | 3.5 | 7.95