## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Bartakkigram Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000093/2023-2024 | 1086/BD | 09/08/2023 | 04/06/2024 | DIPESH BHOWMIK | 822.67 | 387.26 | 47.07 | 65
2 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1836/BD | 18/06/2024 |  | Resource Division | 25.78 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 2888/BD | 06/01/2023 |  | Resource Division | 37.69 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Payment for the quotation of New Connection of PH NO-I of Bartakkigram PWSS under Harirampur CCC. |  |  | BILL/03664/2023-2024 | BP-2023-24-636 | 06/03/2024 |  | W.B.S.E.D.C.LTD | 3.04 | 0 | 0 | null
5 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Payment for the quotation of New Connection of PH NO-II of Bartakkigram PWSS under Harirampur CCC |  |  | BILL/03665/2023-2024 | BP-2023-24-637 | 06/03/2024 |  | W.B.S.E.D.C.LTD | 3.03 | 0 | 0 | null
6 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Bartakkigram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012731) | Assistant Engineer - I | Junior Engineer-01 | ORD/000350/2023-2024 | 2340/MLMD | 26/07/2023 | 23/11/2023 | NUPUR CHANDRA HALDER | 38.61 | 8.97 | 23.24 | 50
Total | [13 empty] | 930.82 | 396.23 | 42.57