## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Dangram Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16562 | Augmentation | Sinking of Tubewell, Restoration of Distribution System, Laying of pipe line in connection with 3rd TW, Pump House, Boundary Wall & Repairing works for Augmentation of Dangram Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000221/2022-2023 | 3817/BD | 23/03/2023 | 06/06/2023 | PRADIP KUMAR PAUL | 155.13 | 100.47 | 64.76 | 88
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Dangram Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16562 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1487/BD | 19/09/2023 |  | Resource Division | 3.86 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Source Augmentation of Dangram Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16562 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Danagram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016072) | Assistant Engineer - I | Junior Engineer-01 | ORD/000443/2023-2024 | 2454/MLMD | 04/08/2023 | 02/12/2023 | PABITRA MANDAL | 12.87 | 10.49 | 81.46 | 100
4 | DAKSHIN DINAJPUR |  | Malda Mechanical | Source Augmentation of Dangram Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16562 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Dangram , Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001876/2023-2024 | 4003201055 | 22/08/2023 | 20/11/2023 | W.B.S.E.D.C.LTD | 8.09 | 4.04 | 50 | 100
Total | [13 empty] | 179.94 | 115 | 63.91