## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for twenty four nos. PWSS in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | SM/17180 |  | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Dhumpara and adjacent Water Supply Schemes at Kushmandi Block in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015913) | Assistant Engineer - I | Junior Engineer-01 | ORD/000195/2023-2024 | 2135/MLMD | 07/07/2023 | 03/10/2028 | DAS CONSTRUCTION | 20.9 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for twenty four nos. PWSS in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | SM/17180 |  | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Deulbari and adjacent Water Supply Schemes at Kushmandi Block in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015913) | Assistant Engineer - I | Junior Engineer-01 | ORD/000196/2023-2024 | 2134/MLMD | 07/07/2023 | 03/10/2028 | B.K. ENTERPRISE | 41.63 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for twenty four nos. PWSS in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | SM/17180 |  | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Chakramprasad and adjacent Water Supply Schemes at Balurghat Block in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015913) | Assistant Engineer - I | Junior Engineer-01 | ORD/000745/2023-2024 | 2809/MLMD | 17/08/2023 | 13/11/2028 | A.K. INDUSTRIES | 69.71 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for twenty four nos. PWSS in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | SM/17180 |  | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Danagram and adjacent Water Supply Schemes at Harirampur Block in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015913) | Assistant Engineer - I | Junior Engineer-01 | ORD/000760/2023-2024 | 2810/MLMD | 17/08/2023 | 13/11/2028 | AMITAVA CHAKRABORTY | 20.29 | 9.11 | 44.93 | 89
5 | DAKSHIN DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for twenty four nos. PWSS in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | SM/17180 |  | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Dhalpara and adjacent Water Supply Schemes at Hili Block in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015913) | Assistant Engineer - I | Junior Engineer-01 | ORD/000762/2023-2024 | 2808/MLMD | 17/08/2023 | 13/11/2028 | THE BUSINESS ENGINEERS INDIA | 13.53 | 6.02 | 44.48 | 89
Total | [13 empty] | 166.06 | 15.13 | 9.11