## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10305 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Kahala and Baharal GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000425/2022-2023 | 3196/MD | 27/12/2022 | 12/03/2023 | KANAN CONSTRUCTION ENTERPRISE | 137.91 | 130.75 | 94.81 | 100
2 | MALDAH |  | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10305 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Debipur GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000463/2022-2023 | 38/MD | 16/01/2023 | 01/04/2023 | MILLENNIUM ENTERPRISR | 114.95 | 77.05 | 67.03 | 67
3 | MALDAH |  | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10305 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Ratua GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000493/2022-2023 | 392/MD | 01/02/2023 | 17/04/2023 | M/S TAPAS KUMAR CHAKRABORTY | 122.55 | 58.4 | 47.65 | 100
4 | MALDAH |  | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. | SM/10305 | Anganwadi | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 531/MD | 03/03/2022 |  | Resource Division | 37.83 | 0 | 0 | 0
Total | [13 empty] | 413.24 | 266.21 | 64.42