## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10382 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Sripur-I, Sripur-II & Maharajpur GP of Ratua-II Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000012/2023-2024 | 1643/MD | 13/04/2023 | 27/06/2023 | USHA ENTERPRISE | 184.54 | 112.6 | 61.02 | 31
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10382 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pirganj, Paranpur and Araidanga GP of Ratua-II Dev. Block under Malda Division, PHE Dte. | Mr. Prasanta Mandal, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer,Sudip Kumar Mahata, Junior Engineer | ORD/000464/2022-2023 | 39/MD | 16/01/2023 | 01/04/2023 | DEBAPRIYA SAHA | 164.05 | 106.26 | 64.77 | 90
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10382 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pukhuria & Sambalpur GP of Ratua-II Dev. Block under Malda Division, PHE Dte. | Mr. Prasanta Mandal, Assistant Engineer,Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer,Mr. Tilok Roy, Junior Engineer,Sudip Kumar Mahata, Junior Engineer | ORD/000501/2022-2023 | 88/MD | 17/01/2023 | 02/04/2023 | M/S TAPAS KUMAR CHAKRABORTY | 109.21 | 75.46 | 69.1 | 100
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. | SM/10382 | School | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 720/MD | 25/03/2022 |  | Resource Division | 28.67 | 0 | 0 | 0
Total | [13 empty] | 486.48 | 294.33 | 60.5