## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pakuahat GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 8 Nos.) | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000383/2022-2023 | 2678/MD | 17/11/2022 | 16/01/2023 | M/S S. S. ENTERPRISE | 48.42 | 43.28 | 89.4 | 90
2 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bamongola GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 9 Nos.) | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000384/2022-2023 | 2679/MD | 17/11/2022 | 16/01/2023 | SOUNAK ENTERPRISE | 54.47 | 45.24 | 83.06 | 48
3 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Madnaboti GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 9 Nos.) | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000385/2022-2023 | 2680/MD | 17/11/2022 | 16/01/2023 | M/S S. S. ENTERPRISE | 54.47 | 0 | 0 | 91
4 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Gobindapur Moheshpur GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 10 Nos.) | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000386/2022-2023 | 3111/MD | 20/12/2022 | 18/02/2023 | FIDERE MARINE SERVICES PRIVATE LIMITED | 60.57 | 50.22 | 82.91 | 82
5 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Jogdala GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 5 Nos.) | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000387/2022-2023 | 2681/MD | 17/11/2022 | 16/01/2023 | M/S AMIT KUMAR GUPTA | 30.27 | 5.43 | 17.93 | 90
6 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chandpur GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 6 Nos.) | Mr. Amit Biswas, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000388/2022-2023 | 2682/MD | 17/11/2022 | 16/01/2023 | M/S JHA CONSTRUCTION | 36.33 | 29.3 | 80.63 | 90
7 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 722/MD | 25/03/2022 |  | Resource Division | 31.32 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | SM/10389 | School | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 119/MD | 05/01/2024 |  | Resource Division | 13.26 | 0 | 0 | 0
Total | [13 empty] | 329.11 | 173.47 | 52.71