## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Formal work order for the work of Implementation of BETAHAL Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000294/2023-2024 | 2829/MD | 25/07/2023 | 20/04/2024 | M/S ALISA CONSTRUCTIION | 227.07 | 77.94 | 34.33 | 11
2 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000298/2024-2025 | 3444/MD | 11/07/2024 | 25/08/2024 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 18.55 | 0 | 0 | 0
3 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Construction of Boundary Wall at 2nd Tube Well site of Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000313/2024-2025 | 3953/MD | 07/08/2024 | 21/09/2024 | M/S ALISA CONSTRUCTIION | 7.26 | 0 | 0 | 0
4 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer |  | ORD/000373/2022-2023 | 2701/MD | 17/11/2022 | 17/12/2022 | ASHIS CONSTRUCTION | 9.2 | 9.17 | 99.68 | 1
5 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Laying of Distribution of UPVC Pipeline of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000928/2023-2024 | 545/MD | 31/01/2024 | 31/03/2024 | FUTURE | 88.28 | 5.02 | 5.68 | 60
6 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 3916/MD | 06/08/2024 |  | Resource Division | 0.86 | 0 | 0 | 0
7 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 23.84 | 0 | 0 | 0
8 | MALDAH | Harischandrapur - II | Malda Division | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 95/MD | 05/01/2024 |  | Resource Division | 7.39 | 0 | 0 | 0
9 | MALDAH | Harischandrapur - II | Malda Mechanical | BETAHAL Piped Water Supply Scheme | SM/12191 | New | New service connection at Bethal PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/00756/2024-2025 | BP-2024-25-202 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 8.73 | 0 | 0 | null
10 | MALDAH | Harischandrapur - II | Malda Mechanical | BETAHAL Piped Water Supply Scheme | SM/12191 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II and making compound lighting arrangement at T/W no. I of Bethal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013024) | Assistant Engineer - II | Junior Engineer-05 | ORD/000026/2023-2024 | 784/MLMD | 27/04/2023 | 25/08/2023 | DEBAPRIYA SAHA | 26.72 | 14.99 | 56.1 | 71
11 | MALDAH | Harischandrapur - II | Malda Mechanical | BETAHAL Piped Water Supply Scheme | SM/12191 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Betahal PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000093/2023-2024 | 3004232800 | 17/05/2023 | 15/08/2023 | W.B.S.E.D.C.LTD | 4.96 | 4.96 | 100 | 0
Total | [13 empty] | 422.87 | 112.08 | 26.51