## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal - I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Formal work order for the work of Implementation of NABAGRAM Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000027/2023-2024 | 1838/MD | 02/05/2023 | 27/01/2024 | R. K. ENTERPRISE | 587.5 | 203.84 | 34.7 | 30
2 | MALDAH | Chanchal - I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Laying of Distribution Line, Providing FHTC, Construction of Pump House at Nabagram Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000142/2024-2025 | 2903/MD | 07/06/2024 | 06/08/2024 | M/S FOUR STAR CONSTRUCTION | 92.58 | 0 | 0 | 0
3 | MALDAH | Chanchal - I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Construction of Boundary Wall at 2nd Tube Well site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000158/2024-2025 | 2933/MD | 10/06/2024 | 10/07/2024 | M/S BHARATI CONSTRUCTION | 7.23 | 0 | 0 | 0
4 | MALDAH | Chanchal - I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Nabagram PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation,Mr. Tilok Roy, Junior Engineer | ORD/000304/2024-2025 | 3450/MD | 10/07/2024 | 24/08/2024 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 0 | 0
5 | MALDAH | Chanchal - I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Additional Laying Distribution of UPVC pipe line of NABAGRAM Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000959/2023-2024 | 710/MD | 09/02/2024 | 25/03/2024 | RATAN KARMAKAR | 4.11 | 1.93 | 46.98 | 70
6 | MALDAH | Chanchal - I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 21.33 | 0 | 0 | 0
7 | MALDAH | Chanchal - I | Malda Division | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 89/MD | 05/01/2024 |  | Resource Division | 18.48 | 0 | 0 | 0
8 | MALDAH | Chanchal - I | Malda Mechanical | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Nabagram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013452) | Assistant Engineer - II | Junior Engineer-05 | ORD/000766/2023-2024 | 2566/MLMD | 04/08/2023 | 02/12/2023 | DAS ENTERPRISE. | 29.85 | 12.51 | 41.9 | 84
9 | MALDAH | Chanchal - I | Malda Mechanical | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of NABAGRAM PWSS, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001016/2023-2024 | 3004407809 | 11/09/2023 | 10/12/2023 | W.B.S.E.D.C.LTD | 12.15 | 12.15 | 100 | 100
10 | MALDAH | Chanchal - I | Malda Mechanical | NABAGRAM Piped Water Supply Scheme | SM/12767 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Nabagram, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-05 | ORD/001886/2023-2024 | 3004460870 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.46 | 1.73 | 50 | 100
Total | [13 empty] | 787.13 | 232.16 | 29.49