## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Formal work order for the work of Implementation of ARAZI JALSA Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000046/2023-2024 | 2008/MD | 17/05/2023 | 11/02/2024 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1160.94 | 493.13 | 42.48 | 35
2 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Construction of Boundary Wall at 2nd Tube Well site of Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000178/2024-2025 | 2953/MD | 10/06/2024 | 10/07/2024 | SIVRAM ENTERPRISE | 8.72 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Construction of Boundary Wall at Head Work site of Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000265/2024-2025 | 3213/MD | 27/06/2024 | 27/07/2024 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.89 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 11.31 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 29/MD | 04/01/2024 |  | Resource Division | 20.4 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Arazi Jalsa Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013468) | Assistant Engineer - II |  | ORD/000505/2023-2024 | 2575/MLMD | 04/08/2023 | 02/12/2023 | NIRMAN. | 26.75 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001899/2023-2024 | 3004481943 | 08/11/2023 | 06/02/2024 | W.B.S.E.D.C.LTD | 9.23 | 6.72 | 72.78 | 100
8 | MALDAH | Gazole | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001900/2023-2024 | 3004481907 | 08/11/2023 | 06/02/2024 | W.B.S.E.D.C.LTD | 4.21 | 4.21 | 100 | 100
Total | [13 empty] | 1263.45 | 504.06 | 39.9