## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Ratua - I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-65C/6570 for the Month of JUNE 2023 under Malda Division PHE Dte. |  |  | BILL/00296/2023-2024 | BP-2023-24-159 | 18/08/2023 |  | UTTAM KUMAR GHOSH | 0.39 | 0 | 0 | 0
2 | MALDAH | Ratua - I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Formal work order for the work of Augmentation of RATUA ZONE-II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000053/2023-2024 | 1999/MD | 17/05/2023 | 11/02/2024 | NIRMAN | 550.19 | 53.14 | 9.66 | 30
3 | MALDAH | Ratua - I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-II Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000681/2021-2022 | 647/MD | 22/03/2022 | 06/04/2022 | ENVIROTECH SOLUTIONS | 3.67 | 3.42 | 93.16 | 1
4 | MALDAH | Ratua - I | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 121/MD | 06/01/2024 |  | Resource Division | 54.12 | 0 | 0 | 0
5 | MALDAH | Ratua - I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | New service connection at RATUA (ZONE II) PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) |  |  | BILL/00761/2024-2025 | BP-2024-25-197 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 4.16 | 0 | 0 | null
6 | MALDAH | Ratua - I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | New service connection at RATUA (ZONE II) PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) |  |  | BILL/00762/2024-2025 | BP-2024-25-198 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 4.6 | 0 | 0 | null
7 | MALDAH | Ratua - I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. |  | Junior Engineer-03 | ORD/000120/2024-2025 | 1200/MLMD | 02/04/2024 | 02/06/2024 | SUBRATA SAHA | 0.78 | 0 | 0 | 0
8 | MALDAH | Ratua - I | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/14097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Ratua (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011274) | Assistant Engineer - II | Junior Engineer-05 | ORD/000507/2023-2024 | 2578/MLMD | 04/08/2023 | 02/12/2023 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.37 | 13.6 | 40.76 | 81
Total | [13 empty] | 651.27 | 70.16 | 10.77