## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Construction of Boundary Wall at head work site of Jotgopal Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000201/2024-2025 | 2988/MD | 11/06/2024 | 11/07/2024 | SHREE BISHNU CONSTRUCTION | 24.3 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Formal work order for the work of Augmentation of JOTGOPAL Piped Water Supply Scheme at Englishbazar Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000235/2023-2024 | 2710/MD | 14/07/2023 | 09/04/2024 | SHREE BISHNU CONSTRUCTION | 192.85 | 31.63 | 16.4 | 25
3 | MALDAH |  | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 95m Deep at Jotegopal PWSS under Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000255/2024-2025 | 3199/MD | 27/06/2024 | 11/08/2024 | ABHIJIT PAUL | 8.36 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JOTGOPAL Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000484/2022-2023 | 1132/MD | 20/03/2023 | 04/05/2023 | S. R. ENTERPRISE | 4.14 | 4.12 | 99.46 | 100
5 | MALDAH |  | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 9.73 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 10.86 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 822/MD | 21/02/2024 |  | Resource Division | 7.67 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Quotation Payment against Jote Gopal JL NO-49 Under Fulbari ccc Under Malda District |  |  | BILL/03627/2023-2024 | BP-2023-24-626 | 04/03/2024 |  | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | null
9 | MALDAH |  | Malda Mechanical | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Augmentation of Jotgopal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008179) | Assistant Engineer - II | Junior Engineer-03 | ORD/000244/2023-2024 | 2261/MLMD | 18/07/2023 | 15/11/2023 | SUBRATA KUMAR DAS. | 13.48 | 4.74 | 35.19 | 0
10 | MALDAH |  | Malda Mechanical | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | SM/14190 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II of Augmentation of Jotgopal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008179) | Assistant Engineer - II | Junior Engineer-03 | ORD/000249/2023-2024 | 2220/MLMD | 18/07/2023 | 16/10/2023 | TAPAN BISWAS. | 12.3 | 5.54 | 45.06 | 40
Total | [13 empty] | 287.23 | 46.03 | 16.03