## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15108 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for SAILPUR Piped Water Supply Scheme at Englishbazar Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer,Shreya Das, Junior Engineer | ORD/000700/2022-2023 | 1157/MD | 20/03/2023 | 04/05/2023 | S. R. CONSTRUCTION | 18.8 | 17 | 90.39 | 79
2 | MALDAH |  | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15108 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 96.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAILPUR Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000709/2022-2023 | 1167/MD | 20/03/2023 | 19/04/2023 | ABHIJIT PAUL | 6.21 | 6.04 | 97.26 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15108 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sailpur Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000759/2022-2023 | 1306/MD | 23/03/2023 | 07/05/2023 | M/S A. B. CONSTRUCTION | 4.14 | 2.06 | 49.71 | 95
4 | MALDAH |  | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15108 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 775/MD | 20/02/2024 |  | Resource Division | 1.85 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15108 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of source augmentation of Sailpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/016471) | Assistant Engineer - II | Junior Engineer-03 | ORD/000578/2023-2024 | 2627/MLMD | 10/08/2023 | 06/02/2024 | KUNDU CONSTRUCTION. | 10.52 | 5.23 | 49.73 | 70
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15108 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Sailpur, Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/001625/2023-2024 | 3004454388 | 09/10/2023 | 07/01/2024 | W.B.S.E.D.C.LTD | 7.69 | 7.69 | 100 | 100
Total | [13 empty] | 49.21 | 38.02 | 77.25