## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15112 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Sadlichalk Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000196/2024-2025 | 2900/MD | 07/06/2024 | 07/07/2024 | SAYEM ENTERPRISE | 2.12 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15112 | Augmentation | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000574/2022-2023 | 765/MD | 17/02/2023 | 19/03/2023 | RABIUL ISLAM | 6.89 | 6.87 | 99.77 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15112 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of SADLICHAK Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000720/2022-2023 | 1178/MD | 20/03/2023 | 19/04/2023 | JAYA ENTERPRISE | 12.03 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15112 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer | ORD/000754/2022-2023 | 1302/MD | 23/03/2023 | 07/05/2023 | SOFIKUL ISLAM | 4.19 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15112 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Sadlichak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016501) | Assistant Engineer - II | Junior Engineer-05 | ORD/000581/2023-2024 | 2630/MLMD | 10/08/2023 | 06/02/2024 | FUTURE | 11.43 | 4.61 | 40.31 | 80
Total | [13 empty] | 36.66 | 11.48 | 31.32