## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000029/2023-2024 | 1840/MD | 02/05/2023 | 16/06/2023 | SARIF BUILDERS | 12.75 | 0.85 | 6.67 | 100
2 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000554/2022-2023 | 1179/MD | 21/03/2023 | 05/05/2023 | M/S STAR INDIA CONSTRUTION | 85.22 | 57.69 | 67.7 | 48
3 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Construction of R.C.C. Culvert (Approach) infront of Head Works Site of AIHO ZONE-I Piped Water Supply Scheme under Malda Division PHE Dte. In the district of Malda. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000613/2023-2024 | 4142/MD | 11/10/2023 | 10/11/2023 | M/S STAR INDIA CONSTRUTION | 1.12 | 0.55 | 49.48 | 100
4 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Acceptance cum formal work order for Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000672/2022-2023 | 1211/MD | 22/03/2023 | 18/09/2023 | M/S FRIENDS CONSTRUCTION & CO. | 91.59 | 64.22 | 70.12 | 65
5 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-1 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000984/2023-2024 | 979/MD | 04/03/2024 | 18/04/2024 | S. R. CONSTRUCTION | 28.24 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 8.74 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Aiho(zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017676) | Assistant Engineer - II |  | ORD/000583/2023-2024 | 2632/MLMD | 10/08/2023 | 06/02/2024 | MUKHERJEE ART CENTRE | 25.83 | 0 | 0 | 0
Total | [13 empty] | 253.49 | 123.32 | 48.65