## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-IVB Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000079/2023-2024 | 2094/MD | 02/06/2023 | 27/02/2024 | M/S N. C. SARKAR | 392.9 | 54.39 | 13.84 | 23
2 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-1 Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000368/2023-2024 | 3057/MD | 09/08/2023 | 08/09/2023 | A. L. ENGINEERING SOLUTION | 9.17 | 4.28 | 46.62 | 100
3 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-2 of Manikchak Block of Malda District under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000369/2023-2024 | 3058/MD | 09/08/2023 | 08/09/2023 | A. L. ENGINEERING SOLUTION | 9.16 | 3.98 | 43.49 | 100
4 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 82.40M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVB Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000964/2023-2024 | 826/MD | 28/02/2024 | 25/10/2024 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 197.84 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | Construction of Boundary Wall at 2nd Tubewell Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/001028/2023-2024 | 1254/MD | 15/03/2024 | 14/04/2024 | A.K. AGENCY | 7.58 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 84.6 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | QUOTATION PAYMENT FOR UTTARCHANDIPUR ZONE IV B T/W NO XIV UNDER MANIKCHAK CCC UNDER MALDA DISTRICT |  |  | BILL/01742/2024-2025 | BP-2024-25-435 | 07/08/2024 |  | W.B.S.E.D.C.LTD | 8.28 | 0 | 0 | null
8 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15193 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XIV,XV and Arsenic Iron Removal Plant at Uttar Chandipur(Zone-IV B) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019390) | Assistant Engineer - II | Junior Engineer-03 | ORD/000649/2023-2024 | 2683/MLMD | 11/08/2023 | 07/02/2024 | A.G ENTERPRISE. | 71.71 | 0 | 0 | 0
Total | [13 empty] | 781.26 | 62.65 | 8.02