## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Formal work order for the work of Augmentation of ADINA ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000119/2023-2024 | 2322/MD | 08/06/2023 | 04/03/2024 | M/S TRILOCHAN CONSTRUCTION CO | 348.95 | 67.03 | 19.21 | 35
2 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000683/2021-2022 | 648/MD | 22/03/2022 | 06/04/2022 | TECHVISION | 3.04 | 3.01 | 98.95 | 1
3 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Construction of Boundary Wall at Head Work site of Adina Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000888/2023-2024 | 162/MD | 08/01/2024 | 22/02/2024 | M/S PARIMAL DAS | 21.89 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 34.17 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Adina Zone-I, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03698/2023-2024 | BP-2023-24-676 | 11/03/2024 |  | W.B.S.E.D.C.LTD | 8.67 | 0 | 0 | null
6 | MALDAH |  | Malda Mechanical | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Adina Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011889) | Assistant Engineer - II |  | ORD/000599/2023-2024 | 2719/MLMD | 14/08/2023 | 08/02/2029 | SUNRISE ENGINEERING CORPORATION. | 28.74 | 0 | 0 | 0
Total | [13 empty] | 445.46 | 70.04 | 15.72