## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Construction of Boundary Wall at 2nd Tube Well site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000181/2024-2025 | 2956/MD | 10/06/2024 | 10/07/2024 | HANNAN BUILDERS PVT. LTD. | 7.92 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Construction of Boundary Wall at Head Work site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000270/2024-2025 | 3228/MD | 28/06/2024 | 28/07/2024 | HANNAN BUILDERS PVT. LTD. | 27.72 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Formal work order for the work of Implementation of PARAHAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000316/2023-2024 | 2951/MD | 02/08/2023 | 28/04/2024 | HANNAN BUILDERS PVT. LTD. | 1038.77 | 313.82 | 30.21 | 30
4 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 814/MD | 21/02/2024 |  | Resource Division | 47.82 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | PARAHAR PWSS | SM/18432 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03696/2023-2024 | BP-2023-24-674 | 11/03/2024 |  | W.B.S.E.D.C.LTD | 5.86 | 0 | 0 | null
6 | MALDAH | Gazole | Malda Mechanical | PARAHAR PWSS | SM/18432 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03697/2023-2024 | BP-2023-24-675 | 11/03/2024 |  | W.B.S.E.D.C.LTD | 6.41 | 0 | 0 | null
Total | [13 empty] | 1134.5 | 313.82 | 27.66