## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Formal work order for the work of Implementation of BABUPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000360/2023-2024 | 3033/MD | 09/08/2023 | 05/05/2024 | M/S UDYOG & CO. | 1331.07 | 335.73 | 25.22 | 30
2 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 815/MD | 21/02/2024 |  | Resource Division | 49.72 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Mechanical | BABUPUR PWSS | SM/18433 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03682/2023-2024 | BP-2023-24-665 | 11/03/2024 |  | W.B.S.E.D.C.LTD | 3.41 | 0 | 0 | null
4 | MALDAH | Gazole | Malda Mechanical | BABUPUR PWSS | SM/18433 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03683/2023-2024 | BP-2023-24-666 | 11/03/2024 |  | W.B.S.E.D.C.LTD | 3.75 | 0 | 0 | null
5 | MALDAH | Gazole | Malda Mechanical | BABUPUR PWSS | SM/18433 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Babupur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014434) | Assistant Engineer - II |  | ORD/000375/2023-2024 | 2383/MLMD | 28/07/2023 | 24/01/2024 | GHOSH BROTHERS... | 41.99 | 0 | 0 | 0
Total | [13 empty] | 1429.94 | 335.73 | 23.48