## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Formal work order for the work of Implementation of HATNAGAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000372/2023-2024 | 3104/MD | 10/08/2023 | 06/05/2024 | M/S GUPTA ENTERPRISE | 628.84 | 199.78 | 31.77 | 50
2 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 247/MD | 10/01/2024 |  | Resource Division | 8.25 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 817/MD | 21/02/2024 |  | Resource Division | 32.68 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Hatnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/020336) | Assistant Engineer - II |  | ORD/000755/2023-2024 | 2822/MLMD | 17/08/2023 | 13/02/2024 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 31.01 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001893/2023-2024 | 3004466995 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.46 | 3.46 | 100 | 100
6 | MALDAH | Gazole | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001894/2023-2024 | 3004466956 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 4.45 | 0.49 | 11.08 | 100
Total | [13 empty] | 708.69 | 203.73 | 28.75