## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Formal work order for the work of Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion of all civil, electrical and mechanical works including all allied and related works of Sub- Surface Water Based Piped Water Supply Scheme in Bamangola block of Malda district followed by three (3) months trial run and five (05) year operation and maintenance. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000584/2023-2024 | 3993/MD | 06/10/2023 | 29/12/2024 | ENGINEERING PROJECTS (INDIA) LIMITED (A GOVERNMENT OF INDIA ENTERPRISE) | 12347.61 | 399.89 | 3.24 | 7
2 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 834/MD | 21/02/2024 |  | Resource Division | 3626.73 | 0 | 0 | 0
3 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quoation Payment For Bamongola Zone-V, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00751/2024-2025 | BP-2024-25-174 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 6.26 | 0 | 0 | null
4 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quotation Payment For Bamongola Zone-II, T/W-1 Under Bamongola CCC Under the district of Malda. |  |  | BILL/00752/2024-2025 | BP-2024-25-175 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 3.94 | 0 | 0 | null
5 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quoation Payment For Bamongola Zone-III, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00753/2024-2025 | BP-2024-25-176 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 3.8 | 0 | 0 | null
6 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quoation Payment For Bamongola Zone-IV, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00754/2024-2025 | BP-2024-25-177 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 6.78 | 0 | 0 | null
7 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quotation Payment For Bamongola Zone-I, T/W-1 Under Bamongola CCC Under the district of Malda. |  |  | BILL/00755/2024-2025 | BP-2024-25-178 | 22/05/2024 |  | W.B.S.E.D.C.LTD | 7 | 0 | 0 | null
8 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Providing Electro-Mechanical components and Making compound lighting arrangement at Ground water based Piped W/S Scheme for different Distribution Zone at Tangon River site (zone-I & II) and Punarbhaba river site (zone-III,IV & V) under Bamongola Sub Surface Water Based Piped Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000734/2023-2024 | 2694/MLMD | 11/08/2023 | 07/02/2024 | DEY ENTERPRISE.. | 80.84 | 12.46 | 15.41 | 30
Total | [13 empty] | 16082.97 | 412.35 | 2.56