## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 90mm dia distribution Pipeline and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahara Para, Master Para under Baliadanga distribution Zone of Southern Sector under Malda Arsenic Area W/S Division, P.H.E.Dte., Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000121/2024-2025 | 1251/MAAD | 24/06/2024 | 09/07/2024 | THREE BROTHERS CONSTRUCTION & CO. | 1.62 | 0 | 0 | 0
2 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of distribution Pipeline from Kaliachak Rail Gate to Khaltipur & Master Para, Alipur Bamba More, Baliadanga near Kaliachak-I BDO Office and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khaltipur under Baliadanga distribution Zone of Southern Sector under Malda Arsenic Area W/S Division, P.H.E.Dte., Malda | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000123/2024-2025 | 1254/MAAD | 24/06/2024 | 23/08/2024 | THREE BROTHERS CONSTRUCTION & CO. | 26.35 | 0 | 0 | 0
3 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 04/02/2025 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 20
4 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) at Nayagram (Baishnabnagar) under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000269/2023-2024 | 3070/MAAD | 14/12/2023 | 12/02/2024 | UNITED FRIENDS UMEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD | 4.97 | 0 | 0 | 100
5 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Karmakarpara under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000270/2023-2024 | 3071/MAAD | 14/12/2023 | 12/02/2024 | DEY CONSTRUCTIONS | 9.92 | 3.61 | 36.44 | 100
6 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 90 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) from 17 mile bandh to Kamartola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000272/2023-2024 | 3072/MAAD | 14/12/2023 | 12/02/2024 | MD. TALEB ALI | 16.82 | 8.41 | 50 | 100
7 | MALDAH |  | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | SM/11912 | Retrofitting | Laying of 125 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) from Old 18 mile to Chamagram, Chhoto chamagram, Poladtola, Ajimtola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000275/2023-2024 | 3075/MAAD | 14/12/2023 | 19/05/2024 | ACHARYYA CONSTRUCTION | 29.1 | 0 | 0 | 100
Total | [13 empty] | 24012.03 | 12.02 | 0.05