## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED | SM/15143 | Augmentation | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of capacity 52.0 Cum/ Hr at Gopalpur Water Supply Scheme Zone-I under Malda Arsenic Area W/S Division, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000262/2020-2021 | 128/MAAD | 21/01/2021 | 18/10/2021 | MILLENNIUM ENTERPRISE | 139.74 | 111.09 | 79.5 | 80
2 | MALDAH |  | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED | SM/15143 | Augmentation | Repairing work of Existing house connection, and Laying of damage UPVC Pipeline at Budhia Dubri under Jote Basanta Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer-I | Junior Engineer-IV | ORD/000267/2022-2023 | 1869MAAD | 28/09/2022 | 12/11/2022 | M/S PARIMAL DAS | 6.24 | 5.6 | 89.7 | 1
3 | MALDAH |  | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED | SM/15143 | Augmentation | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 42.00 M³/ Hr. capacity Iron Elimination Plant (Pressure type) for Gopalpur Zone-II Water Supply Scheme at Manikchak Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | Assistant Engineer-I | Junior Engineer-I | ORD/000452/2022-2023 | 401/MAAD | 06/03/2023 | 02/09/2023 | SHREE BISHNU CONSTRUCTION | 18.65 | 4.92 | 26.37 | 54
4 | MALDAH |  | Malda Mechanical | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED | SM/15143 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR GOPALPUR W S SCHEME |  |  | BILL/01073/2023-2024 | BP-2023-24-94 | 13/07/2023 |  | W.B.S.E.D.C.LTD | 1.73 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED | SM/15143 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Arsenic Iron Removal Plant at Gopalpur (Zone-I) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000014/2023-2024 | 763/MLMD | 26/04/2023 | 23/10/2023 | DILIP MAHATO. | 46.07 | 30.43 | 66.05 | 61
Total | [13 empty] | 212.43 | 152.04 | 71.57