## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Laying of Distribution System at Kabirajtola, Chowdhury Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000126/2023-2024 | 1460/MAAD | 26/07/2023 | 24/09/2023 | M/S MANDAL & SONS | 1.83 | 1.47 | 80.18 | 100
2 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Laying of 250mm, 200mm dia DI pipe line and Supply and delivery of all type of specials & valves at Sadipur Piped Water supply scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000128/2024-2025 | 1259/MAAD | 24/06/2024 | 24/07/2024 | BINA CONSTRUCTION | 6.28 | 0 | 0 | 100
3 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000210/2023-2024 | 1575/MAAD | 25/08/2023 | 24/08/2024 | MERCURY ENGINEERING COMPANY | 156.64 | 0 | 0 | 20
4 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sadipur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda(2ND Call) | Assistant Engineer-II | Junior Engineer-II | ORD/000218/2023-2024 | 1706/MAAD | 20/09/2023 | 16/06/2024 | M/S N. C. SARKAR | 203.63 | 0 | 0 | 15
5 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Sadipur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000464/2022-2023 | 553/MAAD | 24/03/2023 | 08/05/2023 | A.L. ENGINEERING SOLUTION | 14.65 | 6.36 | 43.45 | 100
6 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Laying of Distribution System at Kabirajtola, Chowdhury Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000466/2022-2023 | 598/MAAD | 30/03/2023 | 29/05/2023 | M/S MANDAL & SONS | 44.94 | 34.88 | 77.6 | 100
7 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Laying of Distribution System at Pathan Para, Mia Para, Dhanuk Para, Barkattabad, Rishi Para, Molla Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000468/2022-2023 | 600/MAAD | 30/03/2023 | 29/05/2023 | BINA CONSTRUCTION | 43.18 | 33.95 | 78.62 | 100
8 | MALDAH | Kaliachak - II | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Sadipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-II | Junior Engineer-II | ORD/000472/2022-2023 | 610/MAAD | 31/03/2023 | 30/05/2023 | A.L. ENGINEERING SOLUTION | 5.02 | 0 | 0 | 0
9 | MALDAH | Kaliachak - II | Malda Mechanical | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Sadipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017477) | Assistant Engineer - II | Junior Engineer-03 | ORD/000134/2023-2024 | 2051/MLMD | 30/06/2023 | 27/12/2023 | MERCURY ENGINEERING COMPANY. | 63.89 | 20.03 | 31.35 | 30
10 | MALDAH | Kaliachak - II | Malda Mechanical | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | SM/17201 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sadipur , Mothabari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000717/2023-2024 | 3004390610 | 14/08/2023 | 12/11/2023 | W.B.S.E.D.C.LTD | 3.45 | 3.45 | 100 | 100
Total | [13 empty] | 543.52 | 100.13 | 18.42