## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking water Quality Testing Monitoring & Surveillance programme related to Operation & Maintenance in the State of West Bengal under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 1 | ORD/000002/2021-2022 | 1207/MURD | 10/05/2021 | 08/08/2021 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 26.37 | 4.49 | 17.02 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Work order for Supplying & Delivery of laboratory chemicals and glassware to sevabrata & jangipur Sub dist water testing lab............................. under MSD Divn , PHE Dte.. |  |  | ORD/000285/2018-2019 | 622/MURD | 08/03/2019 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.87 | 4.87 | 100 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Work oprder for supplying and delivery of lab chemicals and glassware to Dr. Ambedkar Jana Seva Mission & Salar Sub dist water testing lab................. Under MSD Div , PHE Dte.. |  |  | ORD/000286/2018-2019 | 621/MURD | 08/03/2019 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.85 | 4.85 | 100 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Work order for supplying & Delivery of lab chemicals & glassware to 20 nos water testing la .................................. under MSD Divn , PHE Dte.. |  |  | ORD/000287/2018-2019 | 628/MURD | 08/03/2019 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.78 | 4.78 | 100 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Supplying & Delivery of Lab Chemicals & Glassware to 20 nos water testing Lab......... in state of West Bengal under MSD Divn , PHE Dte.. |  |  | ORD/000288/2018-2019 | 633/MURD | 08/03/2019 |  | SAHA SCIENTIFIC HOUSE | 5 | 4.83 | 96.64 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Supplying & Delivery of Lab Chemicals & Glassware to 20 nos water testing Lab......... in state of West Bengal under MSD Divn , PHE Dte.. |  |  | ORD/000289/2018-2019 | 630/MURD | 08/03/2019 |  | A.S. COMPUTER | 5 | 4.88 | 97.68 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Supplying & Delivery of Lab Chemicals & Glassware to MSD Dist & Lalgola water testing Lab......... in state of West Bengal under MSD Divn , PHE Dte.. |  |  | ORD/000290/2018-2019 | 632/MURD | 08/03/2019 |  | SAHA SCIENTIFIC HOUSE | 5 | 4.87 | 97.49 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Cont. Order of Supply, delivery of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., TNO- 756/20-21/EE |  |  | VCH/000042/2021-2022 | 10/CHE | 22/04/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.87 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Cont. Order of Supply, delivery of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., TNO- 754/20-21/EE |  |  | VCH/000043/2021-2022 | 10/CHE | 22/04/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 3.52 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Cont. Order of Supply, delivery of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., TNO- 755/20-21/EE |  |  | VCH/000044/2021-2022 | 10/CHE | 22/04/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.9 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Supply and refilling analytical gas, spares for hydraulic generator of AAS & different laboratory item....at dist lab, Tno- 812/19-20/EE |  |  | VCH/001180/2019-2020 | null | 11/12/2019 |  | BHARATI CHEMICAL AND SCIENTIFIC WORK | 2.15 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Continuation w/o for supplying & delivering chemical/ reagents and glassware to 20 nos water testing lab under Tno- 353/20-21/EE |  |  | VCH/001544/2020-2021 | null | 11/12/2020 |  | A.S. COMPUTER | 4.88 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to Jalangi and Domkal SD nos water testing lab under Tno- 350/20-21/EE |  |  | VCH/001545/2020-2021 | null | 11/12/2020 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.86 | 0 | 0 | 0
14 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to Ambedkar and salar water testing lab under Tno- 349/20-21/EE |  |  | VCH/001546/2020-2021 | null | 11/12/2020 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.85 | 0 | 0 | 0
15 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to Sevabrata and Jangipur water testing lab under Tno- 352/20-21/EE |  |  | VCH/001547/2020-2021 | null | 11/12/2020 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.87 | 0 | 0 | 0
16 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to different water testing lab under Tno- 351/20-21/EE |  |  | VCH/001548/2020-2021 | null | 11/12/2020 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.9 | 0 | 0 | 0
17 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | CONT ORDER FOR SUPPLYING & DELIVERY OF LABORATORY CHEMICALS AND GLASS WARE...W.T LABS PHE DTE, TNO- 465/20-21/EE |  |  | VCH/001712/2020-2021 | 469/W | 03/03/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.78 | 0 | 0 | 0
18 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | CONT ORDER FOR SUPPLYING & DELIVERY OF LABORATORY CHEMICALS AND GLASS WARE...W.T LABS PHE DTE, TNO- 466/20-21/EE |  |  | VCH/001713/2020-2021 | 469/W | 03/03/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 3.52 | 0 | 0 | 0
19 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., |  |  | VCH/001820/2020-2021 | null | 18/03/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.87 | 0 | 0 | 0
20 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. |  |  | VCH/001821/2020-2021 | null | 18/03/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 3.52 | 0 | 0 | 0
21 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. |  |  | VCH/001822/2020-2021 | null | 18/03/2021 |  | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.9 | 0 | 0 | 0
22 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Further to work order for Extension o Llaying of UPVC pipeleine from Mohidul Molla houses to Jamal Sk house of Jagaipur W/S Scheme under Berhampore Sub Division PHE DTE. Tender no-588 of 20-21 by EE |  |  | VCH/001873/2020-2021 | 458/W | 24/02/2021 |  | DEBIPROSAD DE | 4.98 | 0 | 0 | 0
23 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Holding Awarness programme/campaingning programms at lalgolal GP Billborakopara GP Amdahara GP Kolan GP Kantanagar Mahammadpur GP Amarkundu GP & Shibpur GP in connection with Functional Household Tap Connection FHTC under Murshidabad Div PHE DTE. Tender no-576 of 20-21 by EE |  |  | VCH/001874/2020-2021 | 458/W | 24/02/2021 |  | IMAGIN | 3.51 | 0 | 0 | 0
24 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Day to Day O & M of 3205 KLD and 5820 KLD water treatme t plant of Mahyampur W/S Scheme and surface based W/S Scheme Bweldanga Municipality mouza W/S Scheme under MURD under BSD PHE DTE. period from 01.09.20 to 31.08.21 Tender no-49 of 20-21 by SE/MC |  |  | VCH/001875/2020-2021 | 458/W | 24/02/2021 |  | RAY ENTERPRISES | 16.35 | 0 | 0 | 0
25 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | Restoration of Road for laying of different dia UPVC/DI/CI pipeline at KANTANAGAR area under Improvement work of Kantanagar W/S Scheme under LSD PHE DTE. Tender no-14 of 20-21 by AE/LSD |  |  | VCH/001876/2020-2021 | 458/W | 24/02/2021 |  | SK CONSTRUCTION (NAJIR SK.) | 1.23 | 0 | 0 | 0
26 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | COMPUTER OPERATOR BILL OF AE LSD, TNO- 28/20-21/EE |  |  | VCH/002102/2020-2021 | 506/NP | 23/03/2021 |  | A.K.A ENTERPRISE | 0.46 | 0 | 0 | 0
27 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | COMPUTER OPERATOR BILL OF AE-ISD, TNO- 41/19-20/AEISD |  |  | VCH/002103/2020-2021 | 506/NP | 23/03/2021 |  | MINA DAS | 0.22 | 0 | 0 | 0
28 | MURSHIDABAD |  | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL FOR MONTH FEBRUARY-2021 |  |  | VCH/002104/2020-2021 | 506/NP | 23/03/2021 |  | R.N CLUB LAB | 0.33 | 0 | 0 | 0
Total | [13 empty] | 144.33 | 33.58 | 23.26