## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAZAESAU (Village Code 315629) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000566/2020-2021 | 3012/MURD | 04/12/2020 | 18/01/2021 | SANJAY BISWAS | 26.55 | 18.03 | 67.91 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | SM/08185 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Saktipur ( Village Code -315633) under Saktipur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, P.H.E Dte. Scheme Id - 5185583 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000764/2020-2021 | 45/MURD | 06/01/2021 | 05/07/2021 | CHAKRABORTY CONSTRUCTION | 119.73 | 0 | 0 | 45
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MAHATA (Village Code 315638) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000769/2020-2021 | 3014/MURD | 04/12/2020 | 18/01/2021 | SO-FINE AQUARIUM | 12.76 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village KATAIKONA (Village Code 315631) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000770/2020-2021 | 3013/MURD | 04/12/2020 | 18/01/2021 | MAJUMDER CONSTRUCTION | 35.53 | 0 | 0 | 50
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village MAIN(Village Code 315632) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000771/2020-2021 | 3018/MURD | 04/12/2020 | 18/01/2021 | MAJUMDER CONSTRUCTION | 34.29 | 0 | 0 | 40
Total | [13 empty] | 228.86 | 18.03 | 7.88