## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000261/2020-2021 | 2392/MURD | 18/09/2020 | 02/11/2020 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 0.12 | 1.22 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | Retrofitting | LAYING OF DIFFERENT DIA UPVC PIPELINE AND CCONSTRUCTION OF RCC STANDPOST AT DAKSHIN KHANDA WSS. |  |  | ORD/000296/2018-2019 | 1031/MURD | 01/06/2018 |  | S. ROY & CO. | 27.05 | 0.06 | 0.21 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIMULIA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000469/2021-2022 | 237/KSD | 27/08/2021 | 26/10/2021 | IMAGIN COMMUNICATION | 4.17 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000632/2020-2021 | 2392/MURD | 18/09/2020 | 02/11/2020 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 8.09 | 82.93 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of Village of Harinya, Datta Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, DakshinKhanda (Nos FHTC-4251) (Village code-315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) under DAKSHINKHANDA Ground Water Based Water Supply Scheme and Kagram ( Nos FHTC-3297) (Village code-315714) under Kagram Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0007338400 & 0007773828) | ASSISTANT ENGINEER |  | ORD/001278/2021-2022 | 141/MURD | 19/01/2022 | 18/07/2022 | M/S. S. DAS AND ENTERPRISE | 383.18 | 56.55 | 14.76 | 0.5
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 3632/D/MURD | 23/11/2021 |  | Resource Division | 23.38 | 0 | 0 | 0
Total | [13 empty] | 457.3 | 64.82 | 14.17