## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-A). | ASSISTANT ENGINEER |  | ORD/000034/2022-2023 | 167/JSD | 01/04/2022 | 01/05/2022 | S.D PROJECT | 4.85 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-B). | ASSISTANT ENGINEER |  | ORD/000035/2022-2023 | 168/JSD | 01/04/2022 | 01/05/2022 | S.D PROJECT | 4.81 | 8.19 | 170.46 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-C). | ASSISTANT ENGINEER |  | ORD/000036/2022-2023 | 169/JSD | 01/04/2022 | 01/05/2022 | M/S G.M ENTERPRISE (MD. GOLAM MEHABUB) | 4.84 | 4.83 | 99.7 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-D). | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000037/2022-2023 | 170/JSD | 01/04/2022 | 01/05/2022 | SUMAN ENTERPRISE AND SUMAN AQUA | 4.84 | 3.66 | 75.75 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-E). | ASSISTANT ENGINEER |  | ORD/000048/2022-2023 | 178/JSD | 01/04/2022 | 01/05/2022 | M/S JOY MA BANAMALI | 4.8 | 3.85 | 80.19 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kasiadanga (Village Code -314124) (Part-I) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000294/2021-2022 | 2299/MURD | 02/08/2021 | 01/10/2021 | KISMAT ARA BEGUM | 69.04 | 68.35 | 99.01 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) laying pipeline in connection with under command area of village of BAHARA (Village Code-314123) & KULGACHHI (Village Code-314119) under KASIADANGA Ground water Based Water Supply Scheme for Arsenic Affected Areas of RAGHUNATHGANJ-II Block, under Murshidabad Division,PHE Dte. | ASSISTANT ENGINEER |  | ORD/000341/2022-2023 | 1837/MURD | 13/07/2022 | 10/12/2022 | DHIRENDRANATH MONDAL | 192.87 | 192.68 | 99.91 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kasiadanga ( Village Code -314124) (Part-II) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) | ASSISTANT ENGINEER |  | ORD/000418/2021-2022 | 2595/MURD | 25/08/2021 | 24/10/2021 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 70.36 | 67.32 | 95.68 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | Retrofitting | Laying of UPVC pipeline at village Laxmijola (East Side) in connection with FHTC work under Kasiadanga (Zone-II) Water Supply Scheme under Jangipur Sub-Division,P.H.E. Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001281/2021-2022 | 419./LSD | 31/12/2021 | 30/01/2022 | MARUTI CONSTRUCTION AND CO | 3.8 | 0 | 0 | 0
Total | [13 empty] | 360.19 | 348.88 | 96.86