## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000412/2023-2024 | 2862/MURD | 08/09/2023 | 08/10/2023 | PRADIP KUMAR DAS | 5.94 | 5.94 | 100 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000465/2020-2021 | 547/MURD | 05/02/2021 | 07/03/2021 | PRADIP KUMAR DAS | 39.01 | 0 | 0 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/001337/2021-2022 | 55/JSD | 25/01/2022 | 24/02/2022 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/001338/2021-2022 | 56/JSD | 25/01/2022 | 24/02/2022 | IMAGIN | 4.16 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Mahesail (Village code 313954) & Amuha (Village code 313955) under Mahisail Ground Based Water Supply Scheme for Arsenic Affected Areas of Suti-II Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723341) | ASSISTANT ENGINEER | JUNIOR ENGINEER_SUTI 2 BLOCK | ORD/001636/2021-2022 | 502/MURD | 23/02/2022 | 22/08/2022 | DECON INDIA | 239.71 | 162.32 | 67.72 | 80
Total | [13 empty] | 366.94 | 168.26 | 45.86