## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09836 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 |  | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09836 | Retrofitting | Work order for Supply and Installation of Automatically controlled chlorinator for accurate dosing with allied works of 1 & 2 for Charmahula water supply scheme & 1 & 2 for Basabari water supply scheme, & T/W 3 for Mahadevnagar Z-II Water Supply Scheme under Jangipur Sub Div. Phe DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000301/2018-2019 | 754/MURD | 29/03/2019 | 27/03/2025 | GOUTAM ELECTRICALS (PROP: GOUTAM CHANDRA SARKAR) | 4.81 | 4.81 | 99.98 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09836 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at HUMAIPUR G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000501/2021-2022 | 336/BSD | 27/08/2021 | 26/09/2021 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 100 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09836 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Basabari (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001156/2021-2022 | 2643 /MURD | 27/08/2021 | 26/10/2021 | AZAD ENTERPRISE | 21.66 | 19.85 | 91.63 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09836 | Retrofitting | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Malibari PWSS under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/001720/2021-2022 | 154/ISD | 17/03/2022 | 16/04/2022 | MABCO GEOTEST ASSOCIATES | 1.48 | 1.48 | 100 | 1
Total | [13 empty] | 77.47 | 30.3 | 39.11