## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh | SM/09844 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sinkaipur (Village code 314775) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte Scheme ID 0005019112 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001377/2021-2022 | 1617 / MURD | 28/06/2021 | 27/08/2021 | DAS ENTERPRISE (PROP-DIPAK DAS) | 5.14 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh | SM/09844 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. ( PART-II ) |  |  | VCH/001296/2021-2022 | null | 17/02/2022 |  | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh | SM/09844 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no - 241 of 21-22 by EE MURD |  |  | VCH/001456/2021-2022 | 342-MSD/21-22 | 05/03/2022 |  | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0 | 0
Total | [13 empty] | 13.07 | 0 | 0