## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Edrakpur & Adjoining Mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nowda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000014/2023-2024 | 982/MURD | 10/04/2023 | 09/04/2024 | SANJAY BISWAS | 643.42 | 109.59 | 17.03 | 70
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Edrakpur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000583/2022-2023 | 3067/MURD | 17/11/2022 | 17/12/2022 | M/S B.R. SUPPLIERS | 10.6 | 4.99 | 47.06 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Edrakpur PWSS Scheme, Block - Nowda) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR ENGINEER 1 | ORD/000842/2021-2022 | 3275/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 6.22 | 6.22 | 100 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 1210/MURD/01 | 02/05/2023 |  | Resource Division | 11.39 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000349/2023-2024 | 112/MURD/06 | 11/01/2024 |  | Resource Division | 26.32 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000354/2023-2024 | 305/MURD/3 | 29/01/2024 |  | Resource Division | 9.58 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | NEW CONNECTION EDRAKPU PH-I |  |  | BILL/01625/2023-2024 | 471/WBSEDCL-JJM | 20/03/2024 |  | WBSEDCL | 20.76 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | NEW CONNECTION AT EDRAKPUR PH-1 |  |  | BILL/01647/2023-2024 | null | 18/03/2024 |  | WBSEDCL | 20.76 | 0 | 0 | null
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Edrakpur ground water based water supply scheme under Block- Nowda, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000087/2023-2024 | 1887/MEDB | 16/06/2023 | 14/09/2023 | SRI KRISHNA NIRMAN | 11.66 | 3.72 | 31.95 | 50
Total | [13 empty] | 760.71 | 124.52 | 16.37