## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | Formal Work Order for Augmentation of CHANDPUR Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE | ORD/000521/2022-2023 | 2496/MURD | 30/08/2022 | 27/01/2023 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 388.72 | 59.11 | 15.21 | 70
2 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE | ORD/000844/2021-2022 | 3277/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 14.82 | 0 | 0 | 0.67
3 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | Repair and Renovation of Pump high lift pupm house at head works site of Chandpur water supply scheme under Berhampore Sub Division, P.H.E. Dte. |  | JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE | ORD/001676/2021-2022 | 13/BSD | 10/01/2022 | 09/02/2022 | MASUM CONSTRUCTION | 3.55 | 2.89 | 81.38 | 0
4 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 1811/MURD/04 | 20/06/2024 |  | Resource Division | 21.13 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000303/2023-2024 | 1278/MURD/5 | 10/05/2023 |  | Resource Division | 11.58 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000355/2023-2024 | 305/MURD/04 | 29/01/2024 |  | Resource Division | 10.27 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | CHANDPUR Z-II PH-I |  |  | BILL/01571/2023-2024 | 426/WBSEDCL-JJM | 12/03/2024 |  | WBSEDCL | 22.73 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | NEW CONNECTION CHANDPUR ZONE-II PH-1 |  |  | BILL/01587/2023-2024 | null | 05/03/2024 |  | WBSEDCL | 22.73 | 0 | 0 | null
9 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No._I ,II and III ,Zone-II under Chandpur ground water based water supply scheme under Block_ Nowda Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000027/2023-2024 | 1873/MEDB | 16/06/2023 | 14/09/2023 | B. T. PROJECTS PVT. LTD. | 34.2 | 0 | 0 | 0
Total | [13 empty] | 529.74 | 62 | 11.7