## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/11716 | Augmentation | Renovation of Existing AIRP (Capacity 11 Cu.M) for changing of filter media of 1 No Polishing unit (2.17 M dia x 1.50 M HOS) & 1 No Primary Unit ( 2.17 M dia x 2.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000807/2023-2024 | 616/MURD | 28/02/2024 | 29/03/2024 | M/S BAPPA ENTERPRISE | 13.7 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/11716 | Augmentation | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 11 Cu.M/hr) at Dakhin Sekhalipur W/S Scheme in connection with Augmentation of Dakhin Sekhalipur PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000833/2023-2024 | 783/MURD | 14/03/2024 | 03/04/2024 | M/S BAPPA ENTERPRISE | 7.56 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/11716 | Augmentation | Providing Functional Household Tap Connections (FHTC) with laying of Pipeline for last mile connectivity in village Dakshin Sekhalipur (314102) & Paschim Khandua(314103) Village in connection with Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000891/2022-2023 | 914/MURD | 30/03/2023 | 28/07/2023 | PROSENJIT DAS | 72.6 | 28.24 | 38.9 | 85
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/11716 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/11716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 1167/MURD/5 | 28/04/2023 |  | Resource Division | 0.33 | 0 | 0 | 0
Total | [13 empty] | 175.61 | 28.24 | 16.08